## Road Map
Accounting Software (Xero)
|  |  | Cycle 1 | Cycle 2 | Cycle 3
Application Modules | Feature Backlog | Story Points | Test Completion Date- 04/19/2024 | Test Completion Date- 05/03/2024 | Test Completion Date- 05/10/2024
10. Bills to Pay | 10.1 Awaiting approval | 3 | X
| 10.2 Awaiting payment | 3 |  | X
| 10.3 Create new or repeating bill | 3 |  |  | X
| 10.4 Edit bills or delete bills | 5 |  |  | X
| 10.5 Importing bills | 3 |  | X
| 10.6 Generating new cedit note. | 3 | X
| 10.7 Exporting bills. | 5 |  | X
| 10.8 Automate bill entry. | 3 | X
| 10.9 Upcoming invoice data | 3 |  | X
| 10.10 Scheduled Payments | 2 |  | X
| 10.11 Verification of paid module | 5 | X
| 10.12 Purchases overview | 5 |  | X
| 10.13 Copy contents to bills and sales invoices | 5 |  |  | X
12. Accounting Reports | 12.1 Account transactions and payrolls | 5 | X
| 12.2 Cash payments by vendor | 3 |  | X
| 12.3 Aged payables summary | 3 | X
| 12.4 Aged Receivables Summary | 3 |  | X
| 12.5 Balance Sheet | 3 |  | X
| 12.6 Income statement | 5 |  |  | X
| 12.7 Sales Tax Report | 5 | X
| 12.8 Payables and receivables | 3 |  | X
| 12.9 Reconciliation Reports | 3 | X
| 12.10 Bank Summary and Reconciliation | 3 |  | X
| 12.11 Inventory Item List | 3 | X
| 12.12 Account Summary | 5 |  |  | X
| 12.13 Fixed Asset Reconciliation | 8 |  | X
|  | Velocity | 33 | 41 | 23